## Sheet1
Site | Enrollment Goal | Enrollment Actual | Forms Expected | Forms Complete | Forms Not Complete | Forms Not Expected | Forms Done % | Queries Total | Queries Manual | Queries Open | Queries Responded | Queries Closed | Protocol Deviations | Locked | Locked %
01-Mbagathi Health Centre | 301 | 292 | 2628 | 1295 | 1333 | 0 | 49 | 65 | 0 | 18 | 1 | 47 | 0 | 0 | 0
02-Special Treatment Centre Casino Health Centre | 224 | 75 | 675 | 368 | 307 | 0 | 55 | 24 | 0 | 7 | 0 | 17 | 0 | 0 | 0
03-Coast Provincial General Hospital | 301 | 13 | 117 | 61 | 56 | 0 | 52 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0
04-International Centre for Reproductive Health | 224 | 16 | 144 | 70 | 74 | 0 | 49 | 6 | 0 | 2 | 0 | 4 | 0 | 0 | 0
05-Homa-Bay County Referral Hospital | 302 | 175 | 1574 | 974 | 600 | 1 | 62 | 49 | 0 | 5 | 0 | 44 | 0 | 0 | 0
Summary | 1352 | 571 | 5138 | 2768 | 2370 | 1 | 53.87 | 146 | 0 | 32 | 1 | 114 | 0 | 0 | 0
| Form Monitored |  |  |  | Form Signed
| Required | Done | To Do | Done % | Required | Done | To Do | Done %
01-Mbagathi Health Centre | 1312 | 148 | 1164 | 11 | 1312 | 0 | 1312 | 0
02-Special Treatment Centre Casino Health Centre | 374 | 118 | 256 | 32 | 374 | 0 | 374 | 0
03-Coast Provincial General Hospital | 61 | 0 | 61 | 0 | 61 | 0 | 61 | 0
04-International Centre for Reproductive Health | 72 | 0 | 72 | 0 | 72 | 0 | 72 | 0
05-Homa-Bay County Referral Hospital | 978 | 161 | 817 | 16 | 978 | 0 | 978 | 0
Summary | 2797 | 427 | 2370 | 15 | 2797 | 0 | 2797 | 0